## Sheet1
Activity | Made by | required time in days | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18
PID |  | 2
Current situation | Iva | 1
Desired situation | IVa | 1
MoSCoW | Thom
Costs/benefits/ROI | Arnoud/Thom
Project organisation | Arnoud/Thom
Roles and responsibilities | Arnoud/Thom
Project costs | Arnoud/Thom
Project schedule | Arnoud/Thom | 1
Team contract | Arnoud | 1
2
TD |  | 1
Network design | Batu, Sander, Jandrik | 2
Network configuration | Batu, Sander, Jandrik | 2
System design | Batu, Sander, Jandrik | 2
System configuration | Batu, Sander, Jandrik
FD
Use case diagrams | Thom
Scenarios |  | 1
Activity diagram |  | 1
Implementation plan |  | 1
Outcomes and en goal |  | 1
MoSCoW |  | 1
Project organisation |  | 1
Roles and responsibilities
Implementation scenario
Implementation costs
Implementation schedule |  | 3
Fallback scenario

## Sheet3
Activity | Made by | required time in days | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18
Website |  | 2
Basic script |  | 1
Dojo |  | 1
java
security
Database
create database
Link with website |  | 1
security |  | 1
2
Server |  | 1
Installeren server |  | 2
vmware installeren |  | 2